Project Title: Support to Modernization of Statistics Production in Rwanda (Technical Assistance to National Institute of Statistics NISR)

Stakeholder: National Institute of Statistics of Rwanda (NISR)
Focal Person: 
Location: Kigali, Rwanda

Natural Capital Accounting (NCA) Expert: Nauman ul Haq

## 1. Executive Summary

This report presents a gap analysis of Natural Capital Accounting (NCA) in the NISR Rwanda. The consultancy is being undertaken by Nauman ul Haq under the overall direction and coordination of the National Institute of Statistics of Rwanda (NISR), which serves as the lead national agency for the development and institutionalization of Natural Capital Accounting within the broader National Statistical System (NSS).

# Gap Analysis Report: Natural Capital Accounting Framework in Rwanda

## Documents Reviewed

- Rwanda Natural Capital Accounts – Ecosystems, Land, and Water, Minerals

- NSDS4 Environment & Natural Resources Sector Statistical System (ENRSSS) excerpt

## Current Status of Natural Capital Accounts

According to the ecosystem account document, Rwanda has developed four natural capital accounts:

- Land Account: Published March 2018

- Water Account: Validated May 2019, publication pending

- Minerals Account: Under validation (as of November 2019)

- Ecosystem Account: Under validation (as of November 2019)

## NSDS4 Reference to Natural Capital Accounting

The NSDS4 ENRSSS excerpt explicitly mentions: "The ENRSSS must be well developed and well-coordinated in a way that they supply timely and superior quality data to support evidence-based policy formulation and decision making and facilitate the production of Natural Capital Accounts (NCA) data."

Under future orientation, NSDS4 states ENRSSS will focus on: "Producing timely and good quality data for NCA: these data will enhance the general understanding of the role of environment and natural resources in the Rwanda economy and citizens' well-being."

## Key Gaps Identified

### 1. Data and Information Gaps

The ecosystem account uses land cover data from 2015 (10 years old as of 2025) and acknowledges "scarce data on multiple ecosystem services." The minerals account focuses only on resource flows.

Gap Against NSDS4: NSDS4 ENRSSS identifies 74 indicators (72 from administrative records, 3 from surveys). Current NCA accounts do not demonstrate systematic linkage to these indicators.

### 2. Institutional and Coordination Gaps

Previous accounts relied on project-based Steering Committee with WAVES funding. No evidence of continuation beyond 2019.

Gap Against NSDS4: NSDS4 identifies "Sector Coordination" as a key challenge in ENRSSS, noting "multiple stakeholders including government agencies, research institutions, NGOs, and private entities. Coordinating data collection and sharing across these diverse actors can be complex."

### 3. Capacity and Sustainability Gaps

Heavy reliance on external support (World Bank, University of Rwanda, Netherlands Statistics) for account development.

Gap Against NSDS4: NSDS4 identifies "limited capacity in the sector to collect, analyse, interpret and dissemination data" as a challenge, highlighting need for capacity building programs.

### 4. Data Quality and Timeliness Gaps

Accounts from 2018-2019 remain unpublished or unvalidated. No regular update mechanism established.

Gap Against NSDS4: NSDS4 identifies "Timely availability of ENR data with good quality" as a challenge and emphasizes need for "timely and superior quality data" for NCA production.

### 5. System Integration Gaps

No evidence of integration between NCA and other statistical systems.

Gap Against NSDS4: NSDS4 notes "There are different MIS in the sector that need to be integrated" and emphasizes "Integration of environmental and socioeconomic data" as a challenge.

### 6. Data Dissemination Gaps

Limited accessibility of NCA outputs for policy use.

Gap Against NSDS4: NSDS4 identifies "Data dissemination" as a challenge, stating "Statistical information is not readily accessible to policymakers and researchers and the public."

## Addressing Gaps Through Structured Missions

Mission 1: Data and Institutional Review should assess how existing data aligns with NSDS4's 74 ENRSSS indicators and establish coordination mechanisms to address the sector coordination challenges identified in NSDS4.

Mission 2: Account Review and Analysis should evaluate integration opportunities with existing MIS systems mentioned in NSDS4 (EMIS, Rwanda Water Resources Portal) and document methodological approaches.

Mission 3: Strategic Planning must develop a roadmap aligned with NSDS4's future orientation for ENRSSS, particularly the focus on producing timely and good quality data for NCA.

Mission 4: Implementation Support should establish mechanisms for regular NCA production utilizing NSDS4's emphasis on leveraging technology (remote sensing, GIS, data analytics) and establishing data quality control mechanisms.

## Priority Recommendations

Based on documented gaps and NSDS4 orientations:

- Immediate: Update outdated accounts and complete validation/publication of pending accounts

- Short-term: Establish coordination mechanisms addressing NSDS4's identified challenge of multiple stakeholder coordination

- Medium-term: Build capacity to address NSDS4's identified limitation in data collection, analysis, and interpretation skills

- Long-term: Integrate NCA production with NSDS4's vision for regular, timely, quality data production

## Conclusion

The gap analysis reveals significant disconnects between existing Natural Capital Accounts (2018-2019) and the vision articulated in NSDS4's ENRSSS framework. While NSDS4 recognizes NCA data production as important for understanding environment and natural resources' role in Rwanda's economy, the existing accounts operate with outdated data, incomplete validation, and no regular update mechanism. The challenges identified in NSDS4 - particularly around coordination, capacity, integration, and dissemination - are clearly reflected in the current state of NCA implementation. Addressing these gaps requires systematic intervention aligned with NSDS4's future orientation for the Environment & Natural Resources Statistical System.